SMISSI

School Management Information System

Project Delivery Plan

Timeline & Milestone Schedule

| Prepared for: | Edwin |
| --- | --- |
| Prepared by: | Development Team |
| Date: | March 2026 |
| Version: | 1.0 |

# 1. Project Overview

SMISSI (School Management Information System) is a comprehensive, multi-school management platform built to digitalise and unify every operational department of a secondary school. The system spans 35 role-based web portals across 16 functional modules — covering everything from academic management and fee collection to boarding, health, security, and human resources.

| 35 Role-Based Portals | 16 Functional Modules | 2 Delivery Phases |
| --- | --- | --- |

Development is structured in two sequential phases. Phase 1 focuses on the core platform modules that are essential for daily school operations and revenue management. Phase 2 delivers the extended operational ecosystem that connects every department within the institution.

| Phase 1 — Core Platform March 2026 — 30 April 2026 Authentication, Student Records, Academic Management, Finance, Payroll, Communications, Leadership Dashboards | Phase 2 — Extended Operations 1 May 2026 — 15 June 2026 Boarding, Health, Security, Facilities, ECA, Uniforms, HR, SEN & Counseling, HOD Portal |
| --- | --- |

# 2. Phase 1 — Core Platform

| PHASE 1 ¦ Core Platform | Delivery Window March 2026 — 30 April 2026 |
| --- | --- |

Phase 1 delivers the operational backbone of SMISSI — the systems the school depends on every day. This phase covers the seven core modules that directly impact student management, academic delivery, revenue collection, and staff administration. Completion of Phase 1 marks the point at which the school can fully operate the system for its day-to-day functions.

## 2.1  Modules in Scope

| # | Module | Portals Covered |
| --- | --- | --- |
| 1 | Authentication & Access Control | All 35 portals — login, roles, permissions, multi-school isolation |
| 2 | Student Information Management | Head Teacher, Deputy HM, HOD, Teacher |
| 3 | Academic Management | Teacher Dashboard, Gradebook, Class Management, Report Cards, Examinations Officer |
| 4 | Finance — Fee Management | Finance Dashboard, Fee Capture, Invoice Management, Student Finance Portal, Financial Reports, Audit Trail |
| 5 | Payroll Management | Payroll Dashboard, Teacher Payslip Portal |
| 6 | Communications | Communications Officer Portal |
| 7 | Leadership Dashboards | Head Teacher Dashboard, Deputy HM Portal |

## 2.2  Phase 1 Milestone Schedule

| Week | Milestone | Expected Completion |
| --- | --- | --- |
| Wk 1–2 | Foundation: Authentication, RBAC, Multi-School Architecture, Core Data Models | 4 April 2026 |
| Wk 3–4 | Student Information Management — Registration, Enrollment, Guardian Records | 11 April 2026 |
| Wk 4–5 | Academic Management — Timetables, Attendance Tracking, Gradebook | 18 April 2026 |
| Wk 5–6 | Report Cards, Examinations Management, Academic Portals | 23 April 2026 |
| Wk 6 | Finance — Fee Structures, Fee Capture, Payment Processing (MTN/Airtel) | 25 April 2026 |
| Wk 6–7 | Finance — Invoicing, Reports, Audit Trail, Student Finance Portal | 27 April 2026 |
| Wk 7 | Payroll — Salary Processing, PAYE/NSSF, Payslip Generation, Compliance Reports | 28 April 2026 |
| Wk 7 | Communications — Notices, SMS/Email Broadcasts, Delivery Tracking | 29 April 2026 |
| Wk 7 | Leadership Dashboards — Head Teacher & Deputy HM Portals | 29 April 2026 |
| Wk 7–8 | Phase 1 QA, UAT, Bug Fixes & Client Sign-off | 30 April 2026 |

## 2.3  Phase 1 Deliverables

Upon completion of Phase 1, the school will be fully operational on the following:

- Enrol students and manage their complete academic records digitally

- Mark and track attendance from every classroom, with automated parent alerts

- Generate end-of-term report cards from a reviewed and approved workflow

- Capture and track all fee payments with instant digital receipts

- Process monthly payroll with automatic PAYE and NSSF deductions

- Communicate with all staff, students, and parents via SMS and email

- Provide leadership with real-time dashboards for oversight and approvals

# 3. Phase 2 — Extended Operations

| PHASE 2 ¦ Extended Operations | Delivery Window 1 May 2026 — 15 June 2026 |
| --- | --- |

Phase 2 delivers the complete operational ecosystem of SMISSI, connecting every department — from the boarding house to the security gate — into a single unified platform. Phase 2 begins immediately following client sign-off on Phase 1 and runs concurrently with the school's live use of the Phase 1 systems.

## 3.1  Modules in Scope

| # | Module | Portals Covered |
| --- | --- | --- |
| 8 | Boarding Management | Boarding Master, Head of Boarding, Student Boarding Portal, Parent Portal |
| 9 | Health & Medical | Nursing Portal (Sick Bay) |
| 10 | Security & Gate Access | Gate Guard Portal, Head of Security Dashboard |
| 11 | Facilities & Inventory | Facilities Office, Labs & Workspaces, Store (Teacher View) |
| 12 | Extra-Curricular Activities | ECA Office Portal |
| 13 | Uniform Management | Uniform Office Portal |
| 14 | Human Resources | HR Portal |
| 15 | SEN & Counseling | SEN Teacher Dashboard, School Counselor Portal |
| 16 | Head of Department Portal | HOD Portal |

## 3.2  Phase 2 Milestone Schedule

| Week | Milestone | Expected Completion |
| --- | --- | --- |
| Wk 1–2 | Boarding Management — Room Allocation, Roll Call, Leave Management, Parent Portal | 15 May 2026 |
| Wk 2–3 | Health & Medical — Sick Bay Records, Medication Logs, Referrals | 22 May 2026 |
| Wk 3 | Security & Gate — Student Exit/Return, Visitor Logs, Incident Tracking | 26 May 2026 |
| Wk 3–4 | Facilities & Inventory — Asset Register, Lab Bookings, Store Requisitions | 2 June 2026 |
| Wk 4 | Extra-Curricular Activities — Clubs, Scheduling, Achievements | 5 June 2026 |
| Wk 4 | Uniform Management — Stock, Issuance, Student Allocations | 6 June 2026 |
| Wk 5 | Human Resources — Staff Profiles, Leave, Appraisals, Contracts | 9 June 2026 |
| Wk 5 | SEN & Counseling — Accommodation Plans, Welfare Records, Confidential Access Controls | 11 June 2026 |
| Wk 5 | Head of Department Portal — Curriculum, Schemes of Work, Performance Analytics | 12 June 2026 |
| Wk 6 | Phase 2 QA, UAT, Final Integration Testing & Client Sign-off | 15 June 2026 |

## 3.3  Phase 2 Deliverables

Upon completion of Phase 2, the school will additionally be able to:

- Manage the boarding house end-to-end, with real-time parent visibility

- Track every person who enters or leaves the school gate with full audit records

- Maintain complete medical records for sick bay visits with access controls

- Run the store, labs, and facilities with full inventory control and requisition workflows

- Record and track every student discipline case and counseling session securely

- Coordinate all extra-curricular clubs, activities, and student achievements

- Manage uniform inventory, student allocations, and supplier orders

- Administer staff HR records, leave management, contracts, and appraisals

- Provide HODs with curriculum tools, scheme of work management, and performance analytics

# 4. Technology Overview

The SMISSI platform is built on a modern, enterprise-grade technology stack selected for reliability, scalability, and suitability to the Ugandan operational environment.

| Layer | Technology | Purpose |
| --- | --- | --- |
| Backend | Node.js / NestJS | Enterprise-grade, modular, TypeScript |
| Database | PostgreSQL | Relational integrity for complex school data |
| Authentication | JWT + RBAC | Stateless auth for 20+ user roles |
| Payments | MTN MoMo + Airtel (Pesapal) | Primary payment methods in Uganda |
| SMS | Africa's Talking | Uganda-native SMS — best coverage and rates |
| Email | SendGrid | Receipts, reports, and parent notifications |
| File Storage | AWS S3 / Cloudflare R2 | Report cards, payslips, medical documents |
| Real-time | WebSockets (Socket.io) | Gate alerts, medical events, fee reminders |
| PDF Generation | Puppeteer | Report cards, payslips, invoices |
| Hosting | AWS / DigitalOcean | Scalable cloud with low-latency hosting |

# 5. Key Assumptions & Client Responsibilities

The following are required from the client side for development to proceed smoothly and on schedule. Any delays in these items may impact the delivery timeline.

|  | Items marked as client responsibilities should be completed before the respective phase begins to avoid delays to the delivery schedule. |
| --- | --- |

| # | Responsibility | Required By |
| --- | --- | --- |
| 1 | All 35 HTML/CSS frontend files handed over to the development team | Phase 1 start |
| 2 | Student, staff, class, and fee structure data for setup and testing | Phase 1 Week 2 |
| 3 | URA PAYE tax bands and NSSF contribution rates confirmed | Phase 1 Week 6 |
| 4 | MTN and Airtel merchant payment accounts registered | Phase 1 Week 5 |
| 5 | Africa's Talking SMS account registered | Phase 1 Week 5 |
| 6 | Designated staff available for User Acceptance Testing (UAT) | End of each phase |
| 7 | Domain name confirmed; hosting infrastructure provisioned by dev team | Phase 1 Week 1 |
| 8 | Per-school configuration details (name, logo, admin contacts) provided | Phase 1 Week 1 |

# 6. Security & Compliance Standards

The SMISSI platform is built with security as a foundational requirement, not an afterthought. The following standards are applied across all modules:

| Data Protection - All data transmitted over HTTPS (TLS 1.3) - Passwords hashed with bcrypt — never stored in plain text - JWT tokens with short expiry and refresh token rotation - Medical and counseling records have an additional access layer | Access & Compliance - Role-based access — no user can access data outside their scope - Rate limiting on all API endpoints to prevent abuse - Financial audit logs are immutable — cannot be altered or deleted - Full login audit trail across all portals |
| --- | --- |

# 7. Next Steps

To formally initiate Phase 1 development, the following actions are required:

1.  Client review and approval of this Project Delivery Plan

2.  Confirmation of frontend handover date for all 35 HTML/CSS portal files

3.  Completion of a technical scoping session to finalise the API integration approach

4.  Registration of required third-party accounts (MTN, Airtel, Africa's Talking)

5.  Agreement on UAT process and designated client testing contacts

|  | This document is prepared for client review. All timelines are indicative and will be confirmed following the technical scoping session. Timelines assume timely delivery of all client responsibilities listed in Section 5. |
| --- | --- |

SMISSI — School Management Information System  |  Confidential  |  Development Team  |  March 2026